## Overview - Notes
Regional On-Call Contract UPC & Task Order UPC Instructions for Set-Up In Pool & IPM
In an effort to provide for statewide consistency and accuracy, Programming Divison and Traffic Engineering Division have compiled this guidance on how Regional Contract UPCs and Individal Project / Task Order UPCs should be entered into the Project Pool & IPM. This has been done with input from the Regions, S&C, and Enviromental Divisions. Consistency in entering these projects is critical to ensure the approval processes proceed as necessary. Please follow these instructions in detail.
If you have any questions or see a field that needs improvement, please do a screen print and send to Dee.Audet@vdot.virginia.gov . We will be improving this process and revising this information as this Regional Contracting Model is utilizied.
Links to Helpful Hints:
Programming Division's Inside VDOT Page for general guidance on Projects:
http://insidevdot/C2/Programming/default.aspx?RootFolder=%2fC2%2fProgramming%2fDocument%20Library%2fiPM%20%2d%20Project%20Pool%20Guidelines&View=%7b656CAA62%2d68B9%2d4E5F%2d844B%2d5718F2E54451%7d
Pool Job Tab – Route, Section and Job Numbers
http://insidevdot/C2/Programming/Document Library/iPM - Project Pool Guidelines/Pool_Job_Tab Project Number Designation.xls
Federal Efficiency Agreement
http://insidevdot/C2/Programming/Document%20Library/Federal%20Information/2005%20Safetea-Lu%20Federal%20Efficiencies%20Agreement%20-%20FO%20or%20NFO/EFFICIENCIES%20AGREEMENT_May%2007%20final.doc

## REGIONAL CONTRACTS
REGIONAL On-Call Contracting Method: CONTRACT UPC = UPC Project for Contract Ad Purpose (See next tab for Individual Projects / Task Orders)
STEP | Pool Workflow | TASK | Federal | State | Pool TAB | Field Name | Required to Save for T-UPC | Required to Obtain Perm UPC | Item to Select or set as in Pool | Comment
1 | New | Setup | x | x | General | Description | Yes | Yes | REGIONAL PVMT MRKR/MRKING - DISTRICT NAME | Consistent Descriptions is IMPORTANT for this contract identification: use "REGIONAL 'Asset type' CONTRACT - DIST/REGION NAME (ALL CAPS)
2 | New | Setup | x | x | General | State Project # | No | No | State Project Number | Enter if known
3 | New | Setup | x | x | General | Project Status | Yes | Yes | Unscheduled Construction | Change as needed for schedule
4 | New | Setup | x | x | General | Accomplishment | No | Yes | Regional On-Call Contract | Chose drop down - Regional On-Call Contract
5 | New | Setup | x | x | General | Project Manager | No | Yes | select a name | Changes to Project Coordinator if Locally Admin is selected. District sets
6 | New | Setup | x | x | General | Sponsor | Yes | Yes | select a name | District sets
7 | New | Setup | x | x | General | Schedule Type | No | Yes | No Plan | Regional Contract to use No Plan.
8 | New | Setup | x | x | General | Major Project | No | No | Leave Blank | N/A
9 | New | Setup | x | x | General | Regionally Significant for Air Quality | No | Yes | No | Should be no for Regional On-Calls
10 | New | Setup | x | x | General | Program Manager | Yes | Yes | Operations Planning Division or Programming Division | Depending on funding, should be OPD for most Regional On-Call. (Setting as PD will require STIP Grouping to be set for Construction selection)
11 | New | Setup | x | x | General | Dashboard Contact | Yes | Yes | select a name | District sets
12 | New | Setup | x | x | General | Non-VDOT Project Manager | No | No | Leave Blank | N/A
13 | New | Setup | x | x | General | Structures Present | No | Yes | Defaults to "No" | Part of S&B enhancement. Available when Operations Planning selected as Program Manager. N/A unless work to be done on structures within project limits
13a & 13b | New | Setup | x | x | General | Number of Bridges / Culverts | No | No | Numerical Number and defaults to "0' | Part of S&B enhancement. Available when Operations Planning selected as Program Manager. N/A unless work to be done on structures within project limits
14 | New | Setup | x | x | General | Record Type | Yes | Yes | Budget | "Budget" on Regional Contract, "Project" on Task Order UPC's
15 | New | Setup | x | x | General | Area Location | No | Yes | Set as one of four choices | Rural, 5K to <50K, 50K to 199,999K, >200,000
16 | New | Setup | x | x | General | Functional Classification | No | Yes | Select appropriate | Select the functional classification for the highest amount of potential marking. Select one to establish contract. Each task order project will have it selected also. Use one that applies to FEDERAL.
17 | New | Setup | x | x | General | Federal Highway | No | Yes | NHS or Non-NHS | Select NHS if one roadway is on NHS, otherwise select Non-NHS
18 | New | Setup | x | x | General | Scope of Work | No | Yes | Safety | For TE Regional Traffic Item On-Call projects, select "safety"
19 | New | Setup | x | x | General | Federal Eligibility | Auto | Yes | Federally Eligible | Once set it will change automatically based on selections in pool
20 | New | Setup | x | x | General | Non VDOT Contact Phone | No | No | N/A | N/A
21 | New | Setup | x | x | General | Non VDOT email Address | No | No | N/A | N/A
22 | New | Setup | x | x | General | Maintenance Funded Label | Yes | Yes | Pick appropriate from drop down | OPD requested as part of S&B enhancement. Available when Operations Planning selected as Program Manager. Captures data for Maintenance.
23 | New | Setup | x | x | General / STIP | Environmental Work | Auto | Yes | TBD - BCE/PCE/CE | (Cedar will update automatically)
24 | New | Setup | x | x | General / STIP | Administered By | Yes | Yes | VDOT | Set as VDOT for VDOT Administered projects
25 | New | Setup | x |  | General / STIP | STIP Grouping | No | Yes | Construction - Safety/ITS/Operational Improvements or Maintenance - Traffic and Safety Operations | Identify majority of Contract as being CN or MN Individual Task Order projects will specific whether grouping falls to CN or MN.
26 | New | Setup | x | x | General/ Location | Jurisdiction | Yes | Yes | 3 digits; key or select | Regional Contract use host dist #; if district contract, use appropriate dist #.
27 | New | Setup | x | x | General/ Location | Region | Auto | Yes | Auto from Jurs. | auto populates when jurisdiction is set
28 | New | Setup | x | x | General/ Location | District | Auto | Yes | Auto from Jurs. | auto populates when jurisdiction is set
29 | New | Setup | x | x | General/ Location | Route | Yes | Yes | Use first 4 digits of State Project Number | First 4 digits of State Project Number
30 | New | Setup | x | x | General/ Location | Formatted Route | No | Yes | EX: GR01 | Overwrites Route: First 4 digits of SPN Use Asset Abbrev (GR, PM, SN) with sequence ##s - 01, 02, etc. for your district/region
31 | New | Setup | x | x | General/ Location | Section # | No | No | N/A | N/A
32 | New | Setup | x | x | General/ Location | MPO | no | no | Check to designate MPO | If applical
33 | New | Setup | x | x | General/ Location | MPO | Auto | Yes | Auto from Jurs.
34 | New | Setup | x | x | General/ Location | PDC | Auto | Yes | Auto from Jurs.
35 | New | Setup | x | x | General/ Location | County | no | no | N/A for multiple counties | N/A for multiple counties; drop down selection for single county
36 | New | Setup | x | x | General/ Location | Residency | no | no | N/A for multiple residencies | N/A for multiple Residencies; drop down selection for single Resdency
37 | New | Setup | x | x | General/ Location | Road System | Yes | Yes | MISC | Contract will likely cover all road systems; if only one system, use drop down selection
38 | New | Setup | x | x | General/ Location | Street Name | no | no | N/A | N/A unless only 1 Route
39 | New | Setup | x | x | General/ Location | Start | No | Yes | Various | Needed for Cardinal. Should not be blank.
40 | New | Setup | x | x | General/ Location | From | No | Yes | Various | Needed for Cardinal. Should not be blank.
41 | New | Setup | x | x | General/ Location | Length: | No | No | numerical value | Optional unless SC&D requires it
42 | New | Setup | x | x | General/ Location | Length (MI or KM) | No | No | MI or KM | Optional unless SC&D requires it
43 | New | Setup | x | x | General/ Location | Project Purpose | Yes | Yes | "CONTRACT UPC FOR AD PURPOSE ONLY - Project to be used to advertise REGIONAL CONTRACT to install / replace PVMT MRKR/MRKING across district. Individual projects will be set-up in the future where funding will be allocated & added as a Task Order. This UPC will have NO funding & NO expenses." | IMPORTANT to consistently reference regional contract in project purpose. Example here is specific to pavement markers/ markings guardrail but insert specific asset on contract (Pv Mrking, Signs, etc.) & briefly describe activity & include "CONTRACT UPC FOR ADVERTISEMENT PURPOSE ONLY" ~ 300 Character Limit ~
44 | New | Setup | x | x | Schedule & Estimate | Phase | No | Yes | CN | Must be selected for constuction phase
45 | New | Setup | x | x | Schedule & Estimate | Estimate | No | Yes | $ xxxxxx.xx | You will need to enter the TOTAL amount you anticipate as the contract to be for ALL years.
46 | New | Setup | x | x | Schedule & Estimate | Start Date | No | Yes | Enter AD Date | This will set AD Date until Schedule overwrites.
47 | New | Setup | x | x | Schedule & Estimate | End Date | No | Yes | Enter ECD Date | This will set ECD Date until Site Manager overwrites. Estimated Completion Date can be adjusted if contractor defaults.
48 | New | Setup | x | x | Misc | Traffic Count | No | No |  | misc information only
49 | New | Setup | x | x | Misc | Traffic Count Date | No | No |  | misc information only
50 | New | Setup | x | x | Misc | Designation | No | No |  | misc information only
51 | New | Setup | x | x | Misc | Project Scale | No | No |  | misc information only
52 | New | Setup | x | x | Misc | Design Date | No | No |  | misc information only
53 | New | Setup | x | x | Misc | Percent Truck | No | No |  | misc information only
54 | New | Setup | x | x | Misc | Design Speed | No | No |  | misc information only
55 | New | Setup | x | x | Misc | Primary Consultant | No | No |  | misc information only
56 | New | Setup | x | x | Misc | Design Location | No | No |  | misc information only
57 | New | Setup | x | x | Classification | Primary Classification | No | Yes | Check the box for "Regional On-Call" | (NEW BOX): TED requested as part of pool enhancement. Indicates to multiple divisions that this project will have elements unique to REGIONAL CONTRACT (no funding, no expense, no plans, no enviro) and will have future individual task order UPC /projects that will have these elements.
58 | New | Setup | x | x | Classification | Funding Classification | No | Yes | System Operations | Select any on box that are appropriate based on anticipated future funding type:System Operations, Highway Safety, etc.
59 | New | Setup | x | x | Classification | Additional Classification | No | No | check appropriate boxes for FO/NFO; required in STIP; required in TIP; required in CLRP | check appropreiate boxes for FO/NFO; required in STIP; required in TIP; required in CLRP
60 | New | Setup | x | x | Comments | Comments | No | No | "CONTRACT UPC FOR AD PURPOSE ONLY - Project to be used to advertise REGIONAL CONTRACT to install / replace PVMT MRKR/MRKING across district. Individual projects will be set-up in the future where funding will be allocated & added as a Task Order. This UPC will have NO funding & NO expenses. " | IMPORTANT to consistently reference regional contract in COMMENTS tab. Example here is specific but insert specific asset on contract (Pv Mrking, Signs, etc.) & briefly describe activity. ~300 character limit ~
61 | New | Setup | x | x | STIP | STIP Groupings | No | Yes | check appropriate boxes: required in STIP; required in TIP; required in CLRP | Can use others if it applies.
62 | New | Setup | x | x | STIP | Regionally Significant for air quality | No | No | TBD/Yes/No | chose appropriate
63 | New | Setup | x | x | STIP | Functional Class | No | No | Use drop down box | chose appropriate
64 | New | Setup | x | x | STIP | Environmental Work | No | No | Use drop down box | chose appropriate
65 | New | Setup | x | x | STIP | STIP Grouping | No | No | Use drop down box | chose appropriate
66 | New | Setup | x | x | STIP | Administered By | No | No | Use drop down box | chose appropriate
67 | Candidate | Job Numbers | x | x | Job | Job Number | No | No | Edit to add Each | Set as N501.
68 | Candidate | Funding | x | x | NA | NA | No | No | NA | No Funding Required
69 | Candidate | Active | x | x | General | Workflow | No | No | Active | Request MUST be submitted to Program Team to add to Live SYP so it happens automatically. If done by pool revision it does not add it to Live SYP but would be available for Schedule in iPM and Cedar. At the same time request PD Program Team to reflect non-posting allocations for first three years to cover life of contract. Amounts by year should cover portion of estimate that is aniticpated.
70 | Active | Active | x | x | General | SYP Status | No | No | Auto when added to Live SYP | Done in Live SYP, changes workflow to Active, available for Schedule in iPM.
71 | Active | Federal Number | x |  | Federal | Federal ID | No | No | PD enters Number | Assigned in project pool 5 months prior to AD Date. iPM report used and if the Job Number is setup and Planned AD Dates in Schedule the number should be assigned on time, otherwise the PM may have to request it from the PD Federal Team. Data entered in FMIS - federal data automatically loaded to pool.
72 | Estimate | PD1 | x | x | Revision | Revision | No | No | Worklist | District approval and CO approval will be required if it is created. Should be approved quickly as long as everything in the data systems is correct and up to date.
73 | Estimate | Transfer | x | x | Revision | Revision | No | No | Worklist | NA - No Funding. No Transfer is Needed.
74 | NA | Update | x | x | MISC | Linked UPCs | No | No | Add on Misc Tab | Insert UPC, Route Description of all Individual Task Order UPCs done under contract
75 | NA | OPEN | x | x | NA | NA | NA | NA | NA | Once bid is selected at AWARD the project will be opened to charges because of the system processses that must occur between Transport & SiteManager. EXPENDITURES MUST BE AVOIDED on this Contract UPC. PD has to submit a request to Financial Planning for approval. The approval is to allow deficit spending and the District Finance Section has to agree not to allow expenditures to roll into the FY. Follow district guidelines on processing expenditure journals. IF EXPENSES ARE APPLIED TO THIS PROJECT, NO EXPENDITURES SHOULD BE ON THE PROJECT FOR MORE THAN THREE MONTHS. We CAN NOT allow expenses on these projects where federal funds are NOT obligated. Expenses should occur / must occur on Individual Task order UPCs.

## INDIVIDUAL PROJECTS
REGIONAL On-Call Contracting Method: Individual UPC Project for Task Order (To Implement Regional Contract)
STEP | Pool Workflow | TASK | Federal | State | Pool TAB | Field Name | Required to Save for T-UPC | Required to Obtain Perm UPC | Item to Select or set as in Pool | Comment
1 | New | Setup | x | x | General | Description | Yes | Yes | REGIONAL (PVMT MRKR/MRKING, GUARDRAIL, etc) - RICHMOND - TASK ORDER## | Consistent Descriptions is IMPORTANT for this task identification: use "REGIONAL"; then 'Asset type abbreviation' - then Dist name; then TASK ORDER## (ALL CAPS)
2 | New | Setup | x | x | General | State Project # | No | No | State Project Number | Enter if known
3 | New | Setup | x | x | General | Project Status | Yes | Yes | Unscheduled Construction | Change as needed for schedule
4 | New | Setup | x | x | General | Accomplishment | No | Yes | TASK ORDER | Use TASK ORDER for individual projects
5 | New | Setup | x | x | General | Project Manager | No | Yes | select a name | Changes to Project Coordinator if Locally Admin is selected. District sets
6 | New | Setup | x | x | General | Project Sponsor | Yes | Yes | select a name | District sets
7 | New | Setup | x | x | General | Schedule Type | No | Yes | No Plan | Individial project UPC (Task Orders) will be No Plan Concept.
8 | New | Setup | x | x | General | Major Project | No | No | Leave Blank | N/A
9 | New | Setup | x | x | General | Regionally Significant for Air Quality | Yes | Yes | No | Should be no for Task Orders
10 | New | Setup | x | x | General | Program Manager | Yes | Yes | Operations Planning Division or Programming Division | OPD if Maint Funds Only. Setting as OP will auto trigger the TIP & STIP boxes to not be checked. All 100% MN projects will fall under a seperate STIP Line Item for Maintenance..
11 | New | Setup | x | x | General | Dashboard Contact | Yes | Yes | select a name | District sets
12 | New | Setup | x | x | General | Non-VDOT Project Manager | No | No | Leave Blank | N/A
13 | New | Setup | x | x | General | Structures Present | No | No | Defaults to "No" | Available when Operations Planning selected as Program Manager. Captures data for Maintenance and S&B on bridges. Available on all projects.
13a & 13b | New | Setup | x | x | General | Number of Bridges / Culverts | No | No | Numerical Number defaults to "0" | Avalible when Operations Planning selected as Program Manager. N/A unless work to be done on structures within project limites.
14 | New | Setup | x | x | General | Record Type | Yes | Yes | Project | "Project" on Individual UPC Projects (Task Orders)
15 | New | Setup | x | x | General | Area Location | No | Yes | Set as one of four choices. | Rural, 5K to <50K, 50K to 199,999K, >200,000
16 | New | Setup | x | x | General | Functional Classification | No | Yes | Select appropriate | Select the functional classification for the highest amount of "term" Select one that is federal.
17 | New | Setup | x | x | General | Federal Highway | No | Yes | NHS or Non-NHS | Select NHS if one roadway is on NHS, otherwise select Non-NHS
18 | New | Setup | x | x | General | Scope of Work | No | Yes | SAFETY | For TE Regional Traffic item On-Call projects, select "Safety"
19 | New | Setup | x | x | General | Federal Eligibility | Auto | Yes | Federally Eligible/Non-Federally Eligible/Federally Eligible with Exception | Once set it will change automatically based on selections in pool. Select Task Orders (Federally Eligible/Non-Federally Eligible/Federally Eligible with Exception), according to the FHWA Efficiencies Agreement.
20 | New | Setup | x | x | General | Non-VDOT Contact Phone | No | No | N/A | N/A
21 | New | Setup | x | x | General | Non-VDOT email Address | No | No | N/A | N/A
22 | New | Setup | x | x | General | Maintenance Funded Label | Yes | Yes | Pick Appropriate from Drop Down | Available when Operations Planning selected as Program Manager. Captures data for Maintenance.
23 | New | Setup | x | x | General / STIP | Environmental Work | Auto | Yes | TBD - BCE/PCE/CE | (Cedar will update automatically)
24 | New | Setup | x | x | General / STIP | Administered By | Yes | Yes | VDOT | Set as VDOT
25 | New | Setup | x |  | General / STIP | STIP Grouping | No | Yes | Construction - Safety/ITS/Operational Improvements or Maintenance - Traffic and Safety Operations | Identify majority of Contract as being CN or MN Individual Task Order projects will specific whether grouping falls to CN or MN.
26 | New | Setup | x | x | General/ Location | Jurisdiction | Yes | Yes | 3 digits; key or select | Regional contract use host dist #; if district contract, use appropriate dist #.
27 | New | Setup | x | x | General/ Location | Region | Auto | Yes | Auto from Jurs. | auto populates when jurisdiction is set
28 | New | Setup | x | x | General/ Location | District | Auto | Yes | Auto from Jurs. | auto populates when jurisdiction is set
29 | New | Setup | x | x | General/ Location | Route | Yes | Yes | Use first 4 digits of State Project Number | First 4 digits of State project Number
30 | New | Setup | x | x | General/ Location | Formatted Route | No | Yes | Use Asset Abbrev (GR, PM, SN) with sequence ##s - 01, 02, etc. for your district/region | Overwrites Route: First 4 digits of SPN (Use guidance per SC&D)
31 | New | Setup | x | x | General/ Location | Section # | No | No | N/A | N/A
32 | New | Setup | x | x | General/ Location | MPO | No | No | Check to designate MPO | if applicable
33 | New | Setup | x | x | General/ Location | MPO | Auto | Yes | Auto from Jurs.
34 | New | Setup | x | x | General/ Location | PDC | Auto | Yes | Auto from Jurs.
35 | New | Setup | x | x | General/ Location | County | No | No | N/A for multiple counties | N/A for multiple counties; drop down for single county
36 | New | Setup | x | x | General/ Location | Residency | No | No | N/A for multiple Residencies | N/A for multiple Residencies; drop down for single Residency
37 | New | Setup | x | x | General/ Location | Road System | Yes | Yes | MISC if all road systems | Contract will likely cover all road systems; if only one system, use drop down selection
38 | New | Setup | x | x | General/ Location | Street Names | No | No | N/A | N/A unless only 1 Route
39 | New | Setup | x | x | General/ Location | Start | No | Yes | Various | Needed for Cardinal. Should not be blank.
40 | New | Setup | x | x | General/ Location | From | No | Yes | Various | Needed for Cardinal. Should not be blank.
41 | New | Setup | x | x | General/ Location | Length: | No | No | numberical value | Optional unless SC&D requires it
42 | New | Setup | x | x | General/ Location | Length (MI or KM) | No | No | MI or KM | Optional unless SC&D requires it
43 | New | Setup | x | x | General/ Location | Project Purpose | Yes | Yes | "Project to use REGIONAL CONTRACT UPC #______to install, replace, repair "asset" at various locations." | IMPORTANT to reference Regional Contract UPC in project purpose. State asset type activity & regional contract UPC.
44 | New | Setup | x | x | Schedule & Estimate | Phase | No | Yes | CN | Must be selected
45 | New | Setup | x | x | Schedule & Estimate | Estimate | No | Yes | Enter applicable amt | Verify amounts prior to submitting task order for approval.
46 | New | Setup | x | x | Schedule & Estimate | Start Date | No | Yes | Enter Date sent to SCD for FHWA Authorization | Dates need to be for Task Order
47 | New | Setup | x | x | Schedule & Estimate | End Date | No | Yes | Enter ECD Date | This will set ECD Date until Site Manager overwrites. Date needs to be for the Task Order
48 | New | Setup | x | x | Misc | Traffic Count | No | No |  | misc information only
49 | New | Setup | x | x | Misc | Traffic Count Date | No | No |  | misc information only
50 | New | Setup | x | x | Misc | Designation | No | No |  | misc information only
51 | New | Setup | x | x | Misc | Project Scale | No | No |  | misc information only
52 | New | Setup | x | x | Misc | Design Date | No | No |  | misc information only
53 | New | Setup | x | x | Misc | Percent Truck | No | No |  | misc information only
54 | New | Setup | x | x | Misc | Design Speed | No | No |  | misc information only
55 | New | Setup | x | x | Misc | Primary Consultant | No | No |  | misc information only
56 | New | Setup | x | x | Misc | Design Location | No | No |  | misc information only
57 | New | Setup | x | x | Classification | Primary Classification | No | Yes | Check the box for "Regional On-Call" | (NEW BOX): TED requested as part of pool enhancement. Indicates to multiple divisions that this project will have elements unique to REGIONAL CONTRACT
58 | New | Setup | x | x | Classification | Funding Classification | No | Yes | System Operations | Select any on box that are appropriate based on anticipated future funding type:System Operations, Highway Safety, etc.
59 | New | Setup | x | x | Classification | Additional Classification | No | No | check appropriate boxes for FO/NFO; required in STIP; required in TIP; required in CLRP | check appropreiate boxes for FO/NFO; required in STIP; required in TIP; required in CLRP
60 | New | Setup | x | x | Comments | Comments | No | No | TASK #_____ on Regional Contract UPC #_________ | IMPORTANT to consistently reference Regional Contract in COMMENTS tab. Example here is specific but insert specific asset on contract (Pv Mrking, Signs, etc.) & briefly describe activity. ~300 character limit ~
0
61 | New | Setup | x | x | STIP | STIP Groupings | No | Yes | check appropriate boxes, required in STIP/TIP/CLRP | Can use others if applicable
62 | New | Setup | x | x | STIP | Regionally Significant for Air Quality | No | No | TBD/Yes/No | chose appropriate
63 | New | Setup | x | x | STIP | Functional Classification | No | No | Use drop down box | chose appropriate
64 | New | Setup | x | x | STIP | Environmental Work | No | No | Use drop down box | chose appropriate
65 | New | Setup | x | x | STIP | STIP Grouping | No | No | Use drop down box | chose appropriate
66 | New | Setup | x | x | STIP | Administered By | No | No | Use drop down box | chose appropriate
0
67 | Candidate | Job Numbers | x | x | Job | Job Number | No | No | Edit to add Each | Set as N501
68 | Candidate | Funding | x | x | NA | NA | No | No | NA | Budget Funds or Tranfers Funds by PD 24 (Be sure to request adding it to Live SYP). Distribute funding to the project as a spending plan by FY. See note on Transfer below.
69 | Candidate | Active | x | x | General | Workflow | No | No | Active | Make sure it is added to Live SYP so it happens automatically. If done by pool revision it does not add it to Live SYP but would be available for Schedule in iPM and Cedar.
70 | Active | Active | x | x | General | SYP Status | No | No | Auto when added to Live SYP | Done in Live SYP, changes workflow to Active, available for Schedule in iPM.
71 | Active | Federal Number | x |  | Federal | Federal ID | No | No | PD enters Number | Assigned in project pool approx. 5 months prior to AD Date. iPM report used and if the Job Number is setup and Planned AD Dates in Schedule the number should be assigned on time, otherwise the PM may have to request it from the PD Federal Team. Data entered in FMIS - federal data automatically loaded to pool.
72 | Estimate | PD1 | x | x | Revision | Revision | No | No | Worklist | District approval and CO approval. If change in process is approved will advise of the new process.
73 | Estimate | Transfer | x | x | Revision | Revision | No | No | Worklist | Need 100% - prev and/or spending plan for future years. Always cover expected expenditures in any given year on a project. Prior to submitting the Task Order projects for approval the PM should make sure the funding is in place.
74 | N/A | Update | x | x | MISC | Linked UPCs | No | No | Add on Misc Tab | Only reference the Regional Contract on the individual Task Order projects
75 | N/A | Project Open | x | x | N/A | N/A | N/A | N/A | N/A | When FHWA Authorizes, project will be opened for charges